## Group Leader To-do List
To-do list
To be completed by: |  |  |  | Name: Theophilus Bassaw
Deadline: |  |  |  | Date: 11/30/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read Project Requirements | 2025-11-17 | 2025-11-19 | 2025-11-23 | 6 | Only Theo and Jacelin
100% | Plan and discuss Metadata | 2025-11-20 | 2025-11-23 | 2025-11-25 | 5 | Only Theo and Jacelin
100% | Normalize Database | 2025-11-26 | 2025-11-30 | 2025-11-30 | 4 | Only Theo
100% | Create Presentation | 2025-11-26 | 2025-11-30 | 2025-11-30 | 4 | Mostly Jacelin, with everyone contributing towards the end
100% | Record | 2025-11-30 | 2025-11-30 | 2025-11-30 | 1
100% | Project Submission | 2025-11-30 | 2025-11-30 | 2025-11-30 | 1

## Group Leader Gannt Chart
PROJECT # 3
Theophilus Bassaw
week of mm/dd
Task | Start Date | Days Needed | Completion Date | SUN | MON | TUES | WED | THUR | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN
Read Project Requirements | 2025-11-17 | 6 | 2025-11-23 | bar: FRI to SUN
Plan and discuss Metadata | 2025-11-20 | 5 | 2025-11-25 | bar: FRI to TUE
Normalize Database | 2025-11-26 | 4 | 2025-11-30 | bar: WED to SUN
Create Presentation | 2025-11-26 | 4 | 2025-11-30 | bar: WED to SUN
Record | 2025-11-30 | 1 | 2025-11-30 | bar: SUN
Project Submission | 2025-11-30 | 1 | 2025-11-30 | bar: SUN

## Jacelin Gomez To-do List
To-do list
To be completed by: |  |  |  | Name: Jacelin Gomez
Deadline: |  | Novemeber 30, 2025 |  | Date: November 30, 2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read Project 3 Requirements | 2025-11-22 | 2025-11-22 |  | 1
100% | Run the Script and figure out how to normalize the database | 2025-11-22 | 2025-11-22 |  | 1
100% | Fill out the Metadata spreadsheet that was given | 2025-11-23 | 2025-11-24 |  | 2
100% | Create Presentation Outline and shared it with Group | 2025-11-24 | 2025-11-26 | 2025-11-26 | 3
100% | Start working on Presentation Slides | 2025-11-26 | 2025-11-29 | 2025-11-29 | 4
100% | Adding some finishing touches to the slide | 2025-11-29 | 2025-11-30 | 2025-11-30 | 2
100% | Record Presentation | 2025-11-30 | 2025-11-30 | 2025-11-30 | 1
100% | Submit all Work | 2025-11-30 | 2025-11-30 |  | 1

## Jacelin Gomez Gannt Chart
PROJECT #3
Jacelin Gomez
|  |  |  | week of 11/16 | week of 11/23 | [6 empty] | week of 11/30
|  |  |  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6
Task | Start Date | Days Needed | Completion Date | SAT | SUN | MON | TUE | WED | THU | FRI | Sat | SUN | MON | TUE | WED | THUR | FRI | SAT
Read Project 3 Requirements | 2025-11-22 | 1 | 2025-11-22 | bar: week of 11/16 22 SAT
Run the Script and figure out how to normalize the database | 2025-11-22 | 1 | 2025-11-22 | bar: week of 11/16 22 SAT
Fill out the Metadata spreadsheet that was given | 2025-11-23 | 2 | 2025-11-24 | bar: week of 11/23 23 SUN to week of 11/23 24 MON
Create Presentation Outline and shared it with Group | 2025-11-24 | 3 | 2025-11-26 | bar: week of 11/23 24 MON to week of 11/23 26 WED
Start working on Presentation Slides | 2025-11-26 | 4 | 2025-11-29 | bar: week of 11/23 26 WED to week of 11/23 29 Sat
Adding some finishing touches to the slide | 2025-11-29 | 2 | 2025-11-30 | bar: week of 11/23 29 Sat to week of 11/30 30 SUN
Record Presentation | 2025-11-30 | 1 | 2025-11-30 | bar: week of 11/30 30 SUN
Submit all Work | 2025-11-30 | 1 | 2025-11-30 | bar: week of 11/30 30 SUN

## Mateo Chimbo To Do List
To-do list
To be completed by: |  |  |  | Mateo Chimbo
Deadline: |  |  |  | 2025-11-30
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Preview requirements and guidelines for Project 3 | Nov 22 | Nov 22 |  | 1
100% | Running of SQL script in order to assess our objective and steps to resolution | 2025-11-22 | 2025-11-22 |  | 1
100% | Work your way through metadata spreadsheet that was provided | 2025-11-23 | 2025-11-24 |  | 2
100% | Presentation Outline Creation and Preview with Groupmates | 2025-11-24 | 2025-11-26 | 2025-11-26 | 3
100% | Start of Slides development | 2025-11-26 | 2025-11-29 | 2025-11-29 | 4
100% | Finishing touches to presentation | 2025-11-29 | 2025-11-30 | 2025-11-30 | 2
100% | Presentation Recording | 2025-11-30 | 2025-11-30 | 2025-11-30 | 1
100% | Submission of Work | 2025-11-30 | 2025-11-30 |  | 1

## Mateo Chimbo Gannt Chart
PROJECT #3
Mateo Chimbo
week of mm/dd
Task | Start Date | Days Needed | Completion Date | SAT | SUN | MON | TUES | WED | THURS | FRI | SAT | SUN | MON | TUES | WED | THURS | FRI
Preview requirements and guidelines for Project 3 | 2025-11-22 | 1 | 2025-11-22
Running of SQL script in order to assess our objective and steps to resolution | 2025-11-22 | 1 | 2025-11-22
Work your way through metadata spreadsheet that was provided | 2025-11-23 | 2 | 2025-11-24
Presentation Outline Creation and Preview with Groupmates | 2025-11-24 | 3 | 2025-11-26
Start of Slides development | 2025-11-26 | 4 | 2025-11-29
Finishing touches to presentation | 2025-11-29 | 2 | 2025-11-30
Presentation Recording | 2025-11-30 | 1 | 2025-11-30
Submission of Work | 2025-11-30 | 1 | 2025-11-30

## Rahat Moktadir To Do List
To-do list
To be completed by: |  |  |  | Name: Rahat Moktadir
Deadline: |  | 2025-11-30 |  | Date: November 30, 2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read Project 3 Requirements | 2025-11-22 | 2025-11-22 |  | 1
100% | Run the script and figure out how to normalize the database | 2025-11-22 | 2025-11-22 |  | 1
100% | Fill out the Metadata spreadsheet that was given | 2025-11-23 | 2025-11-24 |  | 2
100% | Created Presentation Outline and shared it with the group | 2025-11-24 | 2025-11-26 | 2025-11-26 | 3
100% | Start working on Presentation slides | 2025-11-26 | 2025-11-29 | 2025-11-29 | 4
100% | Adding some finishing touches to the slides (images, lines, etc.) | 2025-11-29 | 2025-11-30 | 2025-11-30 | 2
100% | Recording the Presentation | 2025-11-30 | 2025-11-30 | 2025-11-30 | 1
100% | Submittin all the work | 2025-11-30 | 2025-11-30 |  | 1

## Rahat Moktadir Gannt Chart
PROJECT 3
Rahat Moktadir
|  |  |  | week of 11/16 | week of 11/23 | [6 empty] | week of 11/30
|  |  |  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6
Task | Start Date | Days Needed | Completion Date | SAT | SUN | MON | TUE | WED | THU | FRI | Sat | SUN | MON | TUE | WED | THUR | FRI | SAT
Read Project 3 Requirements | 2025-11-22 | 1 | 2025-11-22 | bar: week of 11/16 22 SAT
Run the script and figure out how to normalize the database | 2025-11-22 | 1 | 2025-11-22 | bar: week of 11/16 22 SAT
Fill out the Metadata spreadsheet that was given | 2025-11-23 | 2 | 2025-11-24 | bar: week of 11/23 23 SUN to week of 11/23 24 MON
Created Presentation Outline and shared it with the group | 2025-11-24 | 3 | 2025-11-26 | bar: week of 11/23 24 MON to week of 11/23 26 WED
Start working on Presentation slides | 2025-11-26 | 4 | 2025-11-29 | bar: week of 11/23 26 WED to week of 11/23 29 Sat
Adding some finishing touches to the slides (images, lines, etc.) | 2025-11-29 | 2 | 2025-11-30 | bar: week of 11/23 29 Sat to week of 11/30 30 SUN
Recording the Presentation | 2025-11-30 | 1 | 2025-11-30 | bar: week of 11/30 30 SUN
Submittin all the work | 2025-11-30 | 1 | 2025-11-30 | bar: week of 11/30 30 SUN

## Unsa Chaudhry To Do List
To-do list
To be completed by: |  | 2025-11-30 |  | Unsa Chaudhry
Deadline: |  | 2025-11-30 |  | 2025-11-30
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read assignment details + understand what to do | 2025-11-22 | 2025-11-22 |  | 1
100% | Run the files given and identify what needs to be changed | 2025-11-23 | 2025-11-23 |  | 1
100% | Review + Revise Metadata spreadsheet | 2025-11-23 | 2025-11-24 |  | 2
100% | Review Presentation Outline | 2025-11-24 | 2025-11-24 |  | 1
100% | Begin Presenation | 2025-11-24 | 2025-11-26 |  | 2
100% | Finishing touches | 2025-11-29 | 2025-11-30 |  | 2
100% | Presentation Recording | 2025-11-30 | 2025-11-30 |  | 1
100% | Submission | 2025-11-30 | 2025-11-30 |  | 1

## Unsa Chaudhry Gannt Chart
PROJECT 3
Unsa Chaudhry |  |  |  | week of 11/16 | week of 11/23 |  |  |  |  | week of 11/30
|  |  |  | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-29 | 2025-11-30
Task | Start Date | Days Needed | Completion Date | SUN | MON | TUES | WED | THUR | SAT | SUN | SUN | MON | TUE | WED | THU | FRI | SAT
Read assignment details + understand what to do | 2025-11-22 | 1 | 2025-11-22 | bar: 2025-11-22
Run the files given and identify what needs to be changed | 2025-11-23 | 1 | 2025-11-23 | bar: 2025-11-23
Review + Revise Metadata spreadsheet | 2025-11-23 | 2 | 2025-11-24 | bar: 2025-11-23 to 2025-11-24
Review Presentation Outline | 2025-11-24 | 1 | 2025-11-24 | bar: 2025-11-24
Begin Presenation | 2025-11-24 | 2 | 2025-11-26 | bar: 2025-11-24 to 2025-11-26
Finishing touches | 2025-11-29 | 2 | 2025-11-30 | bar: 2025-11-29 to 2025-11-30
Presentation Recording | 2025-11-30 | 1 | 2025-11-30 | bar: 2025-11-30
Submission | 2025-11-30 | 1 | 2025-11-30 | bar: 2025-11-30

## Prachi Purkaystha To Do List
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 6 Gannt Chart
PROJECT #
Name
week of mm/dd
Task | Start Date | Days Needed | Completion Date | SUN | MON | TUES | WED | THUR | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT

## Sameeha Kamal To Do List
To-do list
To be completed by: |  | 2025-11-30 |  | Sameeha Kamal
Deadline: |  | 2025-11-30 |  | 2025-11-30
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Review Project 3 instructions and dataset overview | 2025-11-22 | 2025-11-22 |  | 1
100% | Read related content and chapters | 2025-11-22 | 2025-11-22 |  | 1
100% | Analyze dataset structure using provided scripts | 2025-11-22 | 2025-11-23 |  | 2
100% | Contribute to metadata documentation (tables, keys, schemas) | 2025-11-23 | 2025-11-24 |  | 2
100% | Collaborate on database normalization and schema planning | 2025-11-24 | 2025-11-26 |  | 2
100% | Build initial draft of assigned presentation sections | 2025-11-26 | 2025-11-29 |  | 3
100% | Finalize slide formatting and refine content | 2025-11-29 | 2025-11-30 |  | 2
100% | Record assigned part of the group presentation | 2025-11-30 | 2025-11-30 |  | 1
100% | Confirm submission of final project files | 2025-11-30 | 2025-11-30 |  | 1

## Sameeha Kamal Gannt Chart
PROJECT 3
Sameeha Kamal
week of mm/dd
|  |  |  | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-29 | 2025-11-30
Task | Start Date | Days Needed | Completion Date | SUN | MON | TUES | WED | THUR | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT
Review Project 3 instructions and dataset overview | 2025-11-22 | 1 | 2025-11-22 | bar: 2025-11-22
Read related content and chapters | 2025-11-22 | 1 | 2025-11-22 | bar: 2025-11-22
Analyze dataset structure using provided scripts | 2025-11-22 | 2 | 2025-11-23 | bar: 2025-11-22 to 2025-11-23
Contribute to metadata documentation (tables, keys, schemas) | 2025-11-23 | 2 | 2025-11-24 | bar: 2025-11-23 to 2025-11-24
Collaborate on database normalization and schema planning | 2025-11-24 | 2 | 2025-11-26 | bar: 2025-11-24 to 2025-11-26
Build initial draft of assigned presentation sections | 2025-11-26 | 3 | 2025-11-29 | bar: 2025-11-26 to 2025-11-29
Finalize slide formatting and refine content | 2025-11-29 | 2 | 2025-11-30 | bar: 2025-11-29 to 2025-11-30
Record assigned part of the group presentation | 2025-11-30 | 1 | 2025-11-30 | bar: 2025-11-30
Confirm submission of final project files | 2025-11-30 | 1 | 2025-11-30 | bar: 2025-11-30